## Start Here
Grant Reporting Process Map
See who your grant report depends on, when each step has to start, and where one departure would sink the deadline.
How to use it
| Step 1 | On Setup, enter the report name, funder, frequency, next due date, and how many workdays of cushion you want.
| Step 2 | On Steps, list each step in the order it happens. Name the owner and the backup, then answer the Y/N questions honestly.
| Step 3 | On People, list everyone who owns or backs up a step, spelled the same way as on Steps.
| Step 4 | Read Dashboard. It tells you the latest date to start, how many steps depend on one person, and who to cross-train first.
| Step 5 | SIPOC builds itself from your steps. Use it as the one-page map for your team and your board.
What each tab does
| Setup | Report details and due dates.
| Steps | The process, step by step, scheduled backward from the due date with a risk score per step.
| SIPOC | Suppliers, Inputs, Process, Outputs, Customers. Built automatically from Steps.
| People | Who carries the process, and who is a single point of failure.
| Dashboard | The answers, in one view.
| Formula Guide | Every formula, explained.
Color key
| Tan cell | Your input. Type over the example values.
| White cell | Formula. Don't type here, it updates on its own. The Formula Guide tab lists every one.
The example values are made up to show how the tool works. They are not benchmarks.
Change Maven LLC ¦ mavenshift.co ¦ change_maven@outlook.com ¦ 217-691-6138

## Dashboard
Dashboard
The answers. Everything here is calculated.
Report | Quarterly Performance Report (Example State Agency)
Due date | 2026-10-30
Workdays left until due | 21
Workdays the process takes | 18
Latest date to start step 1 | 2026-10-05
Schedule check | On track if step 1 starts by Oct 5
Steps in the process | 9
Single points of failure | 6
Share of steps with a trained backup | 33.33%
Steps not written down | 6
High-risk steps | 5
Steps running late | 0
Person carrying the most solo steps | Data Coordinator
Steps only that person can do | 4
Verdict | Fragile. Half or more of the steps depend on one person.
First move | Train a backup for Data Coordinator first.

## Setup
Setup
Report details. Everything else in the workbook keys off these cells.
|  |  | Frequency | Months
Report name | Quarterly Performance Report |  | Monthly | 1
Funder | Example State Agency |  | Quarterly | 3
Reporting frequency | Quarterly |  | Twice a year | 6
Next report due date | 2026-10-30 | Pick the real portal deadline, not your internal target. | Annual | 12
Cushion before due date (workdays) | 2 | Workdays you want finished before the deadline, for surprises.
Months between reports | 3
Report after this one is due | 2027-01-30
Internal finish target | 2026-10-28
Workdays left until due | 21
Formulas:
Quarterly Performance Report = IF(OR(B7="",[Quarterly Performance Report, row above]=""),"",EDATE(B7,[Quarterly Performance Report, row above]))

## Steps
Steps
List the steps in order. The schedule runs backward from the internal finish target on Setup.
# | Step | Supplier (who provides the input) | Input needed | Output of this step | Owner | Backup | Backup trained? (Y/N) | Steps written down? (Y/N) | Workdays needed | Impact if it slips (1-5) | Done? (Y/N) | Latest start | Latest finish | Single point of failure? | Risk score | Risk level | Status
1 | Pull service counts from the case management system | Program staff | Client service records | Service count export | Data Coordinator |  | N | N | 2 | 4 | N | 2026-10-05 | 2026-10-06 | YES | 20 | High | Not started yet
2 | Collect outcome survey results | Program staff | Completed surveys | Outcome summary | Program Director | Data Coordinator | Y | Y | 3 | 4 | N | 2026-10-07 | 2026-10-09 | No | 4 | Low | Not started yet
3 | Reconcile spending to the grant budget | Finance | General ledger and receipts | Budget vs. actual | Finance Manager |  | N | N | 3 | 5 | N | 2026-10-12 | 2026-10-14 | YES | 20 | High | Not started yet
4 | Clean and check the data | Data Coordinator | Service export and outcome summary | Verified data set | Data Coordinator |  | N | N | 2 | 4 | N | 2026-10-15 | 2026-10-16 | YES | 20 | High | Not started yet
5 | Draft the narrative | Program leads | Verified data and program highlights | Draft narrative | Program Director | Development Director | Y | N | 3 | 3 | N | 2026-10-19 | 2026-10-21 | No | 6 | Low | Not started yet
6 | Build tables and charts | Data Coordinator | Verified data set | Report tables | Data Coordinator |  | N | N | 1 | 3 | N | 2026-10-22 | 2026-10-22 | YES | 15 | High | Not started yet
7 | Internal review | Leadership team | Draft report | Review comments | Executive Director | Development Director | Y | Y | 2 | 3 | N | 2026-10-23 | 2026-10-26 | No | 3 | Low | Not started yet
8 | Final edits and sign-off | Executive Director | Review comments | Signed report | Executive Director | Finance Manager | N | Y | 1 | 4 | N | 2026-10-27 | 2026-10-27 | YES | 12 | Medium | Not started yet
9 | Submit in the funder portal | Data Coordinator | Signed report | Submission confirmation | Data Coordinator |  | N | N | 1 | 5 | N | 2026-10-28 | 2026-10-28 | YES | 25 | High | Not started yet
Formulas:
Latest start = IF([Step]="","",WORKDAY([Latest finish],-(MAX(1,[Workdays needed])-1)))
Latest finish = IF([Step]="","",IF([Step, row below]="",Setup!$B12,WORKDAY([Latest start, row below],-1)))
Status = IF([Step]="","",IF([Done? (Y/N)]="Y","Done",IF(TODAY()>[Latest finish],"Late",IF(TODAY()>=[Latest start],"Should be underway","Not started yet"))))

## SIPOC
SIPOC
Built from the Steps tab. Don't type here. Each step's customer is the owner of the next step.
Quarterly Performance Report for Example State Agency
# | Suppliers | Inputs | Process step | Outputs | Customer
1 | Program staff | Client service records | Pull service counts from the case management system | Service count export | Program Director
2 | Program staff | Completed surveys | Collect outcome survey results | Outcome summary | Finance Manager
3 | Finance | General ledger and receipts | Reconcile spending to the grant budget | Budget vs. actual | Data Coordinator
4 | Data Coordinator | Service export and outcome summary | Clean and check the data | Verified data set | Program Director
5 | Program leads | Verified data and program highlights | Draft the narrative | Draft narrative | Data Coordinator
6 | Data Coordinator | Verified data set | Build tables and charts | Report tables | Executive Director
7 | Leadership team | Draft report | Internal review | Review comments | Executive Director
8 | Executive Director | Review comments | Final edits and sign-off | Signed report | Data Coordinator
9 | Data Coordinator | Signed report | Submit in the funder portal | Submission confirmation | Example State Agency

## People
People
Everyone who owns or backs up a step. Spell names exactly as on the Steps tab.
Person or role | Steps owned | Steps backed up | Steps only they can do | Workdays owned | Trained backup for | Risk
Data Coordinator | 4 | 1 | 4 | 6 | 1 | Key person risk
Program Director | 2 | 0 | 0 | 6 | 0 | OK
Finance Manager | 1 | 1 | 1 | 3 | 0 | Watch
Executive Director | 2 | 0 | 1 | 3 | 0 | Watch
Development Director | 0 | 2 | 0 | 0 | 2 | OK
Owners on Steps missing from this list | 0

## Formula Guide
Formula Guide
Every calculated cell in this workbook, what it does, and how to rebuild or extend it.
Tab | Cell(s) | What it calculates | Formula (first cell) | To extend
Setup | B10 | Looks up how many months apart reports are, from the frequency table in E3:F7. | =IFERROR(INDEX($F$4:$F$7,MATCH(B6,$E$4:$E$7,0)),"")
Setup | B11 | Next due date after this cycle (due date plus the months between reports). | =IF(OR(B7="",B10=""),"",EDATE(B7,B10))
Setup | B12 | Due date minus the cushion, skipping weekends. The schedule on Steps works backward from this date. | =IF(B7="","",WORKDAY(B7,-B8))
Setup | B13 | Weekdays between today and the due date. Changes every day. | =IF(B7="","",NETWORKDAYS(TODAY(),B7)-1)
Steps | A5:A24 | Step number, shown only when the step has a name. | =IF(B5="","",ROW()-4) | Already filled to row 24. For more steps, insert rows above row 24 and copy the row above down.
Steps | N5:N24 | Latest finish. The last step must finish by the internal target on Setup. Every earlier step must finish the workday before the next one starts. | =IF(B5="","",IF(B6="",Setup!$B$12,WORKDAY(M6,-1))) | Already filled to row 24. For more steps, insert rows above row 24 and copy the row above down.
Steps | M5:M24 | Latest start. Counts back the workdays needed from the latest finish, skipping weekends. | =IF(B5="","",WORKDAY(N5,-(MAX(1,J5)-1))) | Already filled to row 24. For more steps, insert rows above row 24 and copy the row above down.
Steps | O5:O24 | YES when there is no backup, or the backup isn't trained. | =IF(B5="","",IF(OR(G5="",H5<>"Y"),"YES","No")) | Already filled to row 24. For more steps, insert rows above row 24 and copy the row above down.
Steps | P5:P24 | Risk score from 1 to 25. Impact (1-5) times 1, plus 2 if it's a single point of failure, plus 1 if the steps aren't written down, plus 1 if the owner carries more than 3 steps. | =IF(B5="","",K5*(1+IF(O5="YES",2,0)+IF(I5<>"Y",1,0)+IF(COUNTIF($F$5:$F$24,F5)>3,1,0))) | Already filled to row 24. For more steps, insert rows above row 24 and copy the row above down.
Steps | Q5:Q24 | Risk level. 15 or more is High, 8 to 14 is Medium, under 8 is Low. | =IF(B5="","",IF(P5>=15,"High",IF(P5>=8,"Medium","Low"))) | Already filled to row 24. For more steps, insert rows above row 24 and copy the row above down.
Steps | R5:R24 | Status against today's date and the latest start and finish dates. | =IF(B5="","",IF(L5="Y","Done",IF(TODAY()>N5,"Late",IF(TODAY()>=M5,"Should be underway","Not started yet")))) | Already filled to row 24. For more steps, insert rows above row 24 and copy the row above down.
SIPOC | A3 | Map title, from the report name and funder on Setup. | =Setup!B4&" for "&Setup!B5
SIPOC | A5:A24 | Step number from Steps. | =Steps!A5 | Copy the last row down to match the number of rows on Steps.
SIPOC | B5:B24 | Supplier for this step. | =IF(Steps!$B5="","",Steps!C5) | Copy the last row down to match the number of rows on Steps.
SIPOC | C5:C24 | Input for this step. | =IF(Steps!$B5="","",Steps!D5) | Copy the last row down to match the number of rows on Steps.
SIPOC | D5:D24 | The step itself. | =IF(Steps!$B5="","",Steps!B5) | Copy the last row down to match the number of rows on Steps.
SIPOC | E5:E24 | Output of this step. | =IF(Steps!$B5="","",Steps!E5) | Copy the last row down to match the number of rows on Steps.
SIPOC | F5:F24 | Customer. The owner of the next step, or the funder for the last step. | =IF(Steps!$B5="","",IF(Steps!$B6="",Setup!$B$5,Steps!F6)) | Copy the last row down to match the number of rows on Steps.
People | B5:B16 | How many steps this person owns. | =IF(A5="","",COUNTIF(Steps!$F$5:$F$24,A5)) | Filled to row 16. For more people, insert rows above row 16 and copy down.
People | C5:C16 | How many steps they are listed as backup for. | =IF(A5="","",COUNTIF(Steps!$G$5:$G$24,A5)) | Filled to row 16. For more people, insert rows above row 16 and copy down.
People | D5:D16 | Steps they own that have no trained backup. | =IF(A5="","",COUNTIFS(Steps!$F$5:$F$24,A5,Steps!$O$5:$O$24,"YES")) | Filled to row 16. For more people, insert rows above row 16 and copy down.
People | E5:E16 | Total workdays of the process they carry. | =IF(A5="","",SUMIF(Steps!$F$5:$F$24,A5,Steps!$J$5:$J$24)) | Filled to row 16. For more people, insert rows above row 16 and copy down.
People | F5:F16 | Steps they are a trained backup for. | =IF(A5="","",COUNTIFS(Steps!$G$5:$G$24,A5,Steps!$H$5:$H$24,"Y")) | Filled to row 16. For more people, insert rows above row 16 and copy down.
People | G5:G16 | Key person risk when they alone can do 2 or more steps. | =IF(A5="","",IF(D5>=2,"Key person risk",IF(D5=1,"Watch","OK"))) | Filled to row 16. For more people, insert rows above row 16 and copy down.
People | B18 | Counts owners on Steps whose name isn't in this list. Should be 0. If not, add them or fix the spelling. | =SUMPRODUCT((Steps!$F$5:$F$24<>"")*(COUNTIF($A$5:$A$16,Steps!$F$5:$F$24)=0))
Dashboard | B4 | Report and funder from Setup. | =Setup!B4&" ("&Setup!B5&")"
Dashboard | B5 | Due date from Setup. | =Setup!B7
Dashboard | B6 | Weekdays left, from Setup. | =Setup!B13
Dashboard | B7 | Adds up the workdays needed for every step. | =SUM(Steps!J5:J24)
Dashboard | B8 | Earliest of the latest start dates on Steps. | =IF(COUNT(Steps!M5:M24)=0,"",MIN(Steps!M5:M24))
Dashboard | B9 | Compares the latest start date with today. | =IF(B8="","",IF(B8<TODAY(),"Behind. Step 1 should already have started.","On track if step 1 starts by "&TEXT(B8,"mmm d")))
Dashboard | B10 | Counts the steps you listed. | =COUNTA(Steps!B5:B24)
Dashboard | B11 | Steps with no trained backup. | =COUNTIF(Steps!O5:O24,"YES")
Dashboard | B12 | 1 minus single points of failure divided by total steps. | =IF(B10=0,"",1-B11/B10)
Dashboard | B13 | Steps where the written-down answer isn't Y. | =COUNTIFS(Steps!B5:B24,"<>",Steps!I5:I24,"<>Y")
Dashboard | B14 | Steps with a risk level of High. | =COUNTIF(Steps!Q5:Q24,"High")
Dashboard | B15 | Steps past their latest finish date and not done. | =COUNTIF(Steps!R5:R24,"Late")
Dashboard | B16 | Finds the largest count in People column D and returns that person. | =IF(MAX(People!D5:D16)=0,"None",INDEX(People!A5:A16,MATCH(MAX(People!D5:D16),People!D5:D16,0)))
Dashboard | B17 | The largest count in People column D. | =MAX(People!D5:D16)
Dashboard | B19 | Overall verdict from the share of single points of failure. | =IF(B10=0,"Add your steps on the Steps tab.",IF(B11=0,"Resilient. Every step has a trained backup.",IF(B11/B10>=0.5,"Fragile. Half or more of the steps depend on one person.","At risk. Some steps depend on one person.")))
Dashboard | B20 | Names who to cross-train first. | =IF(B11=0,"Keep backups practiced every cycle.","Train a backup for "&B16&" first.")